## Tabelle1
Version | 1.0
Date | 2023-05-02
Area | Subarea | Unique Risk ID | Description of risk | Explain effect of risk | Explain root causes | Impact | Likelihood A | Risk A = Impact * likelihood | Risk A - Category | Detectibility A | Priority A | Existing controls/ mitigation actions | Impact | Likelihood B | Risk B | Risk B - Category | Detectability B | Priority B
[6 empty] | 6 critical | 3 likely |  |  | High | high |  | 6 critcal | 3 likely |  |  | High | high
[6 empty] | 3 major | 2 possible |  |  | Medium | medium |  | 3 major | 2 possible |  |  | Medium | medium
[6 empty] | 1 minor | 1 unlikely |  |  | Low | low |  | 1 minor | 1 unlikely |  |  | Low | low
Transfer of data | data import | RA-R-001 | correct data incorrectly imported into statistical software | data loss, e.g. loss of multiple rows/columns of data from a file | - faulty coding or encoding of the variables (e.g. discrepancies between dictionaries and coding) - in rare cases: lack of metadata/ information - data corruption / system bug on PC: incorrectly copying file - system import functionality (program used - e.g. MS Excel) has limitations | 3 | 2 | 6 | Medium | Medium | P2-Medium | - process (e.g. quality checks, product descriptions of limitations) - guidelines - use of validated and known computerized systems | 3 | 2 | 6 | Medium | High | P3-Low
|  |  |  | altered data, e.g. wrong dates, rounding differences, Umlaute | format issue between software (e.g., date format from .xslx to R) and software versions data corruption | 1 | 2 | 2 | Low | Medium | P3-Low | - guideline | 1 | 1 | 1 | Low | High | P3-Low
| data transfer (between PI, sponsor, statistician, etc.) | RA-R-002 | import of incorrect data (wrong file, wrong data TBD) | results and conclusions from analysis are incorrect, delay in obtaining correct results, issues with publication, potential GCP non-sompliance | negligence, misscommunication resulting in incorrect file chosen | 3 | 2 | 6 | Medium | High | P3-Low | - process (e.g. quality checks) | 3 | 1 | 3 | Medium | High | P3-Low
|  | RA-R-003 | protection of data privacy violated (e.g. no pseudonymisation) | data protection non-compliance / GCP noncompliance | 1) PI responsibility: ignorance/ negligence on PI side resulting in data being sent in error overall mistake and misscommunication; PI unaware that data should not have been sent 2) Statistician sending unblinded data sets due to misscomunication. | 6 | 2 | 12 | High | High | P2-Medium | - guidelines and/or templates - information material - sensitizing Pis and staff to the importance by training | 6 | 2 | 12 | High | High | P2-Medium
| data sharing on (open) platforms | RA-R-004 | import of incorrect data (wrong file, wrong data TBD) | incorrect analysis | negligence, misscommunication resulting in incorrect file chosen | 3 | 2 | 6 | Medium | Medium | P2-Medium | - guidelines and/or templates - information material - sensitizing Pis and staff to the importance by training | 3 | 1 | 3 | Medium | High | P3-Low
|  | RA-R-005 | protection of data privacy violated (e.g. not anonimyzed) | data protection non-compliance / GCP noncompliance | 1) PI responsibility: ignorance/ negligence on PI side resulting in data being sent in error overall mistake and misscommunication; PI unaware that data should not have been sent 2) Statistician sending unblinded data sets due to misscomunication. | 6 | 2 | 12 | High | Medium | P1-High | - process for online sharing - guidelines and/or templates - information material - sensitizing Pis and staff to the importance by training | 6 | 2 | 12 | High | High | P2-Medium
|  | RA-R-006 | incomplete data sharing or documentation | misunderstanding of data and/or structure by third parties | bad documentation lack of process for data sharing lack of understanding/miscommunication on what to share and why | 1 | 3 | 3 | Medium | Medium | P2-Medium | - process - guidelines - templates | 1 | 1 | 1 | Low | High | P3-Low
Initial data analysis | data validation (ensuring it is correctly done, identifying outlyers, subscores, correct variables) | RA-R-007 | incomplete/ absence or inaccurate validation | - inaccurate analysis results in potentially endangering the scientific outcome - waste of resources as correct analysis has to be redone | - lack of process - lack of resources - lack of budget - negligence | 3 | 2 | 6 | Medium | Medium | P2-Medium | - process: e.g. pre-determined data validation plan; review of plan and validation script; documentation and confirmation by PI - training - guidelines for data validation | 3 | 1 | 3 | Medium | Medium | P2-Medium
| data cleaning (transforming data for analysis) | RA-R-008 | data cleaning is done incorrectly/ insufficiently |  | - lack of process, resources, budget negligence - inappropriate/incomplete approach to monitoring (statistical, central, or on-site) - incomplete/incorrect data cleaning approach | 3 | 1 | 3 | Medium | Medium | P2-Medium | - process: e.g. pre-determined data-cleaning plan; review of plan and validation script; documentation and confirmation by PI - training - guidelines for data cleaning | 3 | 1 | 3 | Medium | High | P3-Low
| data wrangling or preparation (calculation; merging, reshaping data for specific area; extracting, splitting variables,.. use of packages) | RA-R-009 | Incorrect preparation/ alteration of data | incorrect results are produced downstream code doesn't work at all | incorrect assumptions about data structure, lack of training/experience, poor programming skills formatting and/or code errors some details are provided on the protocol, others not; => lack of clarity on information? package implementation, versioning and use was incorrect; unclear package documentation | 3 | 2 | 6 | Medium | Medium | P2-Medium | - process (review by second statistician, 4-eye principle, double programming) - training - choice of peronnel - guidelines (programming guidelines) - process: package management | 3 | 1 | 3 | Medium | High | P3-Low
Statistical analysis (final and ad-interim) | Planning (Study Protocol; SAP) | RA-R-010 | incorrect, inappropriate, wrong statistical methods are used (i.e during sample size calculation and/ or planning of analysis) | incorrect method/ chosen method cannot be applied, loss of power, incorrect result, data cannot be collected. compromised scientific quality => error can go unnoticed | - lack of training/experience - unawareness of method - missunderstanding of trial design (language, generall miscommunication) - protocol changes made without being notified - miscommunication between PI and statistician - initial chosen method can no longer be used later in project | 3 | 2 | 6 | Medium | High | P3-Low | - personnel choice and training - guidelines (e.g. international, ICH, FDA) - process (e.g. review/4-eye/group-work) | 3 | 1 | 3 | Medium | High | P3-Low
|  | RA-R-011 | unclear/ambiguous wording or conflicting statements about the method to be used | incorrect conduct/ different than intended execution of analysis | - lack of training/experience - unawareness of method - misunderstanding of trial design (language, generall miscommunication) - miscommunication between PI and statistician - initial chosen method can no longer be used later in project | 3 | 2 | 6 | Medium | High | P3-Low | - peronnel choice and training - process (e.g. review/4-eye/group-work) | 3 | 1 | 3 | Medium | High | P3-Low
| Implementation of analysis | RA-R-012 | faulty analysis | incorrect results trial stopped at interim analysis when it shouldn't | Package errors incorrect method was planned; incomplete/ ambigeous wording of method to be used faulty coding/ programming | 6 | 2 | 12 | High | Medium | P1-High | - training - process (e.g., review, 'explain to a colleague', double programming) - process - package validation | 6 | 1 | 6 | Medium | High | P3-Low
|  | RA-R-013 | staff changeover/ discontinuation | loss of knowledge project execution slowed ( i.e. due to disagreement regarding appropriate method) | lack of (clear) documentation lack or incomplete handover different levels of expertise | 3 | 2 | 6 | Medium | High | P3-Low | - process for documentation including centralized storage - processes for project transfer | 3 | 1 | 3 | Medium | High | P3-Low
| Unblinding | RA-R-014 | unintentional unblinding of study personnel and/or statistician | best case: new trial statistician to be assigned to project => budget impacting PI unblinded: worst case when i.e. safety data is communciated: trial might be stopped | lack of attention unclarity in regards to who should be blinded/ unblinded unclear when unblinding can take place | 6 | 1 | 6 | Medium | High | P3-Low | - process with safeguards against unblinding | 6 | 1 | 6 | Medium | High | P3-Low
Random processes | Simulation | RA-R-015 | simulations based on (quasi) random processes produce different results in different 'runs' | wrong results or uncertainty 'which' results are used for decision making | no/incorrectly set seed improper PRNG algo used or incorrect use. | 6 | 2 | 12 | High | High | P2-Medium | - process: quality control (review/4-eye/double programming) | 6 | 1 | 6 | Medium | High | P3-Low
| Randomization (programming) | RA-R-016 | computational errors | faulty randomisation list | faulty programming no/incorrectly set seed | 6 | 2 | 12 | High | Medium | P1-High | - process: quality control (review/4-eye/double programming) | 6 | 1 | 6 | Medium | High | P3-Low
|  | RA-R-017 | no reproducibility | difficulties in expanding an existing randomisation list | no/incorrectly set seed improper archiving | 6 | 2 | 12 | High | Medium | P1-High | - process: quality control (review/4-eye/double programming) - guidelines/templates | 6 | 1 | 6 | Medium | Medium | P2-Medium
|  | RA-R-018 | incorrect unblinding | quality of study is compromised | no clear guidelines when unblinding may take place, accidental blinding with data base export | 6 | 1 | 6 | Medium | High | P3-Low | - process - guidelines | 6 | 1 | 6 | Medium | High | P3-Low
Reporting | Publication | RA-R-019 | incorrect/incomplete results reported in the study report/ manuscript | publication of incorrect results (results are not visible; incorrectly formatted or displayed, report does not compile, wrong object/ figure is displayed and used) non-publication of the results | - interface between IDE and software incorrect, package errors (bugs in packages/software involved in conversion from R/stats software objects to report) - copy/ paste error (user error) misunderstanding of analysis output (human error) - no or inaccurate review of manuscript, incorrect statistical report, wrong 'building blocks' of the publication delivered (e.g. wrong figure) | 6 | 1 | 6 | Medium | Medium | P2-Medium | - process: software validation | 6 | 1 | 6 | Medium | High | P3-Low
| Reporting to PI | RA-R-020 | incorrect interpretation of results | publication of misleading results non-publication of the results | PI (or less likely, the Statistician) did not understand the results/method properly and wrote the paper with a flawed understanding | 6 | 2 | 12 | High | Medium | P1-High | - training - choice of personnel - process: product review - process / templates: reporting | 6 | 1 | 6 | Medium | High | P3-Low
|  | RA-R-021 | incorrect results delivered | decision making by PI (e.g. trial stop/continuation) is based on wrong results, manuscript is written based on wrong results, embarressment | keeping multiple versions of results, not having a clear 'final' report or its building blocks, lack of order or system for versioning | 6 | 1 | 6 | Medium | Medium | P2-Medium | - process: working instructions - infrastructure: version control | 6 | 1 | 6 | Medium | High | P3-Low
| Reproducibility / dynamic reporting | RA-R-022 | Lack of dynamic reporting leads to changes in data definitions/sets or in steps in data preparation/analysis generating incompatible/non-updated results | - incorrect results after updates - loss of time and resources | - lack of implementation of tools for dynamic reporting - lack of training | 3 | 2 | 6 | Medium | Medium | P2-Medium | - systematic: implimentation of tools for dynamic reporting - process: working process defining the use of dynamic tools - training + guidelines | 3 | 1 | 3 | Medium | High | P3-Low
| Reporting to authorities | RA-R-023 | Incomplete reporting to authorities or incorrect results delivered | - legal implications on responsibles - loss of institute credit - danger to patients - blocked licensing | - lack of templates and/or training in reporting to authorities - non-compliance with guidelines | 6 | 1 | 6 | Medium | High | P3-Low | - templates - process: review and control mechanisms - training + guidelines | 6 | 1 | 6 | Medium | High | P3-Low
Design | Sample Size Calculation | RA-R-024 | inadequate sample size | compromised scientific quality, ethical concerns | wrong assumptions | 6 | 2 | 12 | High | Low | P1-High | - training and choice of personnel - use of guidelines | 6 | 1 | 6 | Medium | Medium | P2-Medium
|  |  |  | compromised scientific quality, ethical concerns | faulty coding | 6 | 1 | 6 | Medium | Medium | P2-Medium | - process: quality control (review/4-eye/double-programming) - training and choice of peronnel | 6 | 1 | 6 | Medium | High | P3-Low
|  |  |  | compromised scientific quality, ethical concerns | wrong choice of method of calculation/simulation (for complex designs) | 6 | 2 | 12 | High | High | P2-Medium | - process (review/group-work) - training and choice of personnel | 6 | 1 | 6 | Medium | High | P3-Low
| Methodology | RA-R-025 | inappropriate design, e.g. superiority instead of non-inferiority, wrong estimand, confounding, attrition bias, collection of the data (operationalizing variables, endpoint definition) | cannot answer the research questions, biased result | lack of training, unqualified personnel | 6 | 1 | 6 | Medium | High | P3-Low | - training and choice of personnel - process (review/group-work) | 6 | 1 | 6 | Medium | High | P3-Low
| Interim Analysis | RA-R-026 | inappropriate design, biased decision maintaining independence, alpha-error | inappropriate/unjustified (non)-stopping of the trial, placing participant in risk (safety issues) | lack of training, lack of process | 6 | 1 | 6 | Medium | Medium | P2-Medium | - process: quality control (review/4-eye/double-programming) - training and choice of peronnel - guidelines | 6 | 1 | 6 | Medium | High | P3-Low
| Randomization (method) | RA-R-027 | wrong type of randomisation | mismatch between planned and performed randomisation, quality of study might be compromised | faulty implementation | 3 | 1 | 3 | Medium | High | P3-Low | - training and choice of personnel - process (review/group-work) | 3 | 1 | 3 | Medium | High | P3-Low
|  | RA-R-028 | breach of allocation concealment | quality of study is compromised | improper archiving of randomisation list, e.g. accessible to other people of study team | 3 | 1 | 3 | Medium | High | P3-Low | - training and choice of personnel - process: safeguard and guidelines | 3 | 1 | 3 | Medium | High | P3-Low
Computer System | Installation (of IDEs and R) | RA-R-029 | IT software installation in incorrect location/ infrastructure (business computers); e.g. R-tools on windows | - will typically lead to warnings, error messages or failure to start the programme or program malfunctioning - loss of time, resource issues - different computers are set-up differently, impacting the conducted analysis - lack of portability (between computers as scripts may not behave in the same way on another computer) | - potential installation by unqualified staff - lack of training of IT resources - software regretion (previously working features no longer work) | 1 | 1 | 1 | Low | High | P3-Low | - process: software management | 1 | 1 | 1 | Low | High | P3-Low
|  | RA-R-030 | Installation of software on personally owned computers. | - will typically lead to warnings, error messages or failure to start the programme or program malfunctioning - loss of time, resource issues - lack of firewall, protection on local personnally owned PC - different computers are set-up differently, impacting the conducted analysis - lack of portability (between computers as scripts may not behave in the same way on another computer) | - software regretion (previously working features no longer work) - use of personally owned computers - potential installation by unqualified staff | 1 | 1 | 1 | Low | High | P3-Low | - process: software management | 1 | 1 | 1 | Low | High | P3-Low
|  | RA-R-031 | different versions of software installed on different computers or at different analysis timepoints | different results produced by different statisticians/machines code not running errors in results due to different system loss of time non-reproducible results older script not running | - no installation or update guidelines - multiple personnel can install software - Installation of software at different timepoints | 3 | 2 | 6 | Medium | Medium | P2-Medium | - process: software management | 3 | 2 | 6 | Medium | High | P3-Low
|  | RA-R-032 | multiple versions of software installed on the same computer | - different results produced when using software versions inconsistently within a project - loss of time - non-reproducible results - older script not running | - no installation or update guidelines - multiple personnel can install software - Installation of software at different timepoints | 1 | 3 | 3 | Medium | High | P3-Low | - process: software management - process: for reproducible analysis - gruidelines and tools: reproducible research | 1 | 2 | 2 | Low | High | P3-Low
|  | RA-R-033 | outdated software | identified bugs or problems in older versions are not corrected less efficient processes packages not available for installation | negligence or lack of process/guideline | 1 | 3 | 3 | Medium | Medium | P2-Medium | - process: software management | 1 | 2 | 2 | Low | High | P3-Low
| Software Qualification and Validation | RA-R-034 | use of unverified or unvalidated software and/or add-on packages/macros | GCP non-compliance | lack or violation of process | 6 | 2 | 12 | High | Medium | P1-High | - process: software management | 6 | 1 | 6 | Medium | High | P3-Low
| Package errors | RA-R-035 | the package provides wrong results for a given method | incorrect results and conclusions | package not programmed correctly package not validated and/or verified | 6 | 2 | 12 | High | Low | P1-High | - process: package management (approval + testing) - process: quality control (review/internal testing/4-eye) - guidelines: choice of packages | 6 | 2 | 12 | High | High | P2-Medium
| interface between IDE and software | RA-R-036 | Improper connection between Inegrated Development Environment (IDE; e.g. R-Studio, Emacs-ESS) and software (e.g. R) results in incorrect results shown in IDE | reported results are incorrect loss of time identifying discrepancies between IDE and statistical software | bug in IDE faulty installation mismatch between IDE version and Software version | 1 | 1 | 1 | Low | High | P3-Low | - process: software management | 1 | 1 | 1 | Low | High | P3-Low
| add on software for reporting | RA-R-037 | add on software has bugs / is version incompatible with the rest of the build chain (E.g. Latex, pandoc, Sweave). | - incorrect resuts or impossible to produce reports - results reported to PI are incorrect | bugs in extra/ add-on software | 3 | 1 | 3 | Medium | High | P3-Low | - process: software management - process: quality control | 3 | 1 | 3 | Medium | High | P3-Low
Reproducibility | Statistical analysis | RA-R-038 | analysis script produces different output to previously reported no possibility of recreating the preiously reported results | compromised scientific quality, later additional analyses difficult, difficulties in transfer of project between statisticians, loss of credibility | changes in software/package versions (including package software dependencies) package not available improper archiving/documentation (incomplete meta-data) different code (e.g. code was changed since report but not documented) | 3 | 2 | 6 | Medium | Medium | P2-Medium | - training - tools and software for reproducible and dynamic reports - tools for version control - process: package management and documentation - process: software installation and management - tools + process: version control | 3 | 1 | 3 | Medium | High | P3-Low
| Software versioning | RA-R-039 | reports are produced using different software environments/versions | different versions of a package lead to different results | version numbers and product environment are not recorded or reproducible. | 3 | 1 | 3 | Medium | Medium | P2-Medium | - process: software and package management - process + tools: documentation of report meta-data | 3 | 1 | 3 | Medium | High | P3-Low
| Archiving | RA-R-040 | Incomplete documentation archived | not possible to recreate report (or results) GCP non-compliance | lack of process negligence | 6 | 1 | 6 | Medium | High | P3-Low | - process | 6 | 1 | 6 | Medium | High | P3-Low
Scientfic integrity | scientific fraud | RA-R-041 | Poor scientific practice (e.g. P-hacking) | - legal implications on responsibles - loss of institute credit - danger to (future) patients - publication of biased or misleading results, more false-positives | Pressure from PIs to generate positive results and publish in high-ranking journals, exerting pressure on us | 6 | 1 | 6 | Medium | High | P3-Low | - training - guidelines - organizational structure (organigram/responsibilities) | 6 | 1 | 6 | Medium | High | P3-Low
| malicious fraud | RA-R-042 | Results are faked, misrepresentation of results, fake data | publication of incorrect results | Pressure to generate positive results and publish in high-ranking journals | 6 | 1 | 6 | Medium | Medium | P2-Medium | - organizational structure - organizational culture - choice and management of personnel - reporting pathways: establishing processes to identify and report malbehavior of collaborators | 6 | 1 | 6 | Medium | Medium | P2-Medium
| non-acknowledgement / no correction of errors | RA-R-043 | Mistakes are found after reporting of results, but are not communicated to study team | publication of incorrect results | fear of being criticized, bad culture of failure | 6 | 2 | 12 | High | Low | P1-High | - organizational structure - organizational culture - personnel training - personnel management (e.g. employee talks to generate healthy working atmosphere) | 6 | 1 | 6 | Medium | Medium | P2-Medium
Risk assissent / Risk A (basic risk, prior to treatment)
Risk analysis after treatment / Risk B (residual risk)
Note on G5: 6 Critical: Death or disability of study subject (Grade 4 and 5 CTCAE Criteria); Sensitive data of several subjects going public (outside of CTU/ Inselspital); Dissemination in the media; Project unfeasible; study validity compromized; financial damage > 100'000 3 Major: Moderate injuries (Grade 2 and 3 CTCAE Criteria); personal data sets of several subjects going public; Dissemination in the University or at Inselspital; secondary analysis not feasible; major protocol deviations (e.g. no informed consent, SUSAR not reported); financial Dammage > 30'000.- 1 Minor: Minor injuries (Grade 1 and 2 CTCAE Criteria);, Personal data of a single subject going public, pseudomized data set going public, Dissemination in project team, inside CTU, Project delay, financial damage >2'000
Note on H5: 3 Likely Risk might occur 3-4/year) 2 Possible Risk might occur 1-2/year 1 Unlikely Risk might occur <1/year)
Note on M5: Priority of handling the risk: Conditional on Risk category and Detectability According To PharmaSUG 2018 paper suggestion TODO : define "definitions" for what high/low/medium means (e.g. always detectible, 1 out of 5 etc." TODO 2: detectability A vs B (after process)
Note on O5: Remains the same as the "impact" before.
Note on P5: 3 Likely Risk might occur 3-4/year) 2 Possible Risk might occur 1-2/year 1 Unlikely Risk might occur <1/year)
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To me, this is more related to the EDC system export procedure. (UTF-8, etc.). Not to a faulty coding from the stat. Root cause is rather linked to not agreed upon on "universal" format.
Note on J28: Coslovsky Michael: Is this low risk? The design of the study could be totally different than planned if randomization is done faultily? I would put it as medium risk at least
Note on L32: Coslovsky Michael: I suggest medium detectibility, but I don't completely understand what is meant, or what the difference is between 'critical' and 'minor/major' (next line)
Note on A57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I would see reproducibility more as a risk than a risk area. Moreover, all the subareas are listed elsewhere. So maybe we can move the rows to other areas? Reply: I tend to agree with Nicole, though specific areas here such as archiving need to then be reallocated; or we find another name for the 'general reproducibility' we mean here.